## Slide 1: Daily document governance report
AGH-ALPHA · Alpha District Development
REPORT DATE
18-10-2026
Project team: PM – S. Rahman || PE – M. Khan || DC – A. Nair || Cost centre CC-3107
ADDED SINCE YESTERDAY
SUBMITTALS
+21
Total
+11
Approved
+4
Resubmit
+1
Rejected
+5
Under review
Chart: 
| Total | Approved | Resubmit | Rejected | Under review
SUBMITTALS | 21 | 11 | 4 | 1 | 5
DRAWINGS
+32
Total
+16
Approved
+4
Resubmit
+2
Rejected
+10
Under review
Chart: 
| Total | Approved | Resubmit | Rejected | Under review
DRAWINGS | 32 | 16 | 4 | 2 | 10
SUBMISSION TOTAL
+53
Total
+27
Approved
+8
Resubmit
+3
Rejected
+15
Under review
Chart: 
| Total | Approved | Resubmit | Rejected | Under review
SUBMISSION TOTAL | 53 | 27 | 8 | 3 | 15
CORRESPONDENCE
+6
Outgoing
+6
Incoming
Chart: 
| Outgoing | Incoming
Correspondence | 6 | 6
CUMULATIVE (TILL DATE)
SUBMITTALS
451
Total
292
Approved
59
Resubmit
20
Rejected
80
Under review
Chart: 
| Total | Approved | Resubmit | Rejected | Under review
SUBMITTALS | 451 | 292 | 59 | 20 | 80
DRAWINGS
583
Total
373
Approved
77
Resubmit
27
Rejected
106
Under review
Chart: 
| Total | Approved | Resubmit | Rejected | Under review
DRAWINGS | 583 | 373 | 77 | 27 | 106
SUBMISSION TOTAL
1,034
Total
665
Approved
136
Resubmit
47
Rejected
186
Under review
Chart: 
| Total | Approved | Resubmit | Rejected | Under review
SUBMISSION TOTAL | 1034 | 665 | 136 | 47 | 186
CORRESPONDENCE
318
Outgoing
291
Incoming
Chart: 
| Outgoing | Incoming
Correspondence | 318 | 291
TILL DATE: APPROVAL & REVIEW
APPROVED STATUS / % OF OVERALL CUM.
Chart: 
| Drawing rev 0 +9 | Drawing rev 1 +4 | Drawing rev 2 +3 | Submittal rev 0 +7 | Submittal rev 1 +2 | Submittal rev 2 +2
% of overall cum. | 24.2 | 9.5 | 2.4 | 18.4 | 7.9 | 1.9
OVERALL UNDER REVIEW
186
Under review (till date)
Chart: 
| Client | Algihaz | Supplier
Under review | 90 | 58 | 38
SUBMISSIONS REVIEW (PENDING DAYS)
Party | ≤7 d | 8–30 d | ≥31 d | Total
Client | 75 | 39 | 13 | 127
Algihaz | 49 | 22 | 9 | 80
Supplier | 29 | 19 | 9 | 57
All parties | 153 | 80 | 31 | 264
d = days · all review statuses combined
TOTAL REJECTED SUBMISSION
47
+3 since yesterday
Chart: 
| Drawing +2 | Materials +1 | Calculation 0 | General 0
Rejected | 27 | 10 | 4 | 6
Detailed report: [PDF report link]
Notes: One-page view for the business. Top band = documents added since yesterday (current minus yesterday). Middle band = cumulative till the report date. Bottom band = approved share by revision, under review by party, pending days and rejected submissions. Sample data.

## Slide 2: Drawings & submittals by discipline
Alpha District Development · 18-10-2026
Drawings · 583
▲ +32 since yesterday
Chart: 
| Civil | Structural | Mechanical | Electrical | Instrumentation
Approved | 126 | 101 | 67 | 58 | 21
Resubmit | 26 | 20 | 14 | 12 | 5
Rejected | 8 | 7 | 6 | 4 | 2
Under Review | 33 | 24 | 21 | 17 | 11
Discipline | Approved | Resubmit | Rejected | Review | Total | Change
Civil | 126 | 26 | 8 | 33 | 193 | ▲+10
Structural | 101 | 20 | 7 | 24 | 152 | ▲+8
Mechanical | 67 | 14 | 6 | 21 | 108 | ▲+6
Electrical | 58 | 12 | 4 | 17 | 91 | ▲+5
Instrumentation | 21 | 5 | 2 | 11 | 39 | ▲+3
Overall | 373 | 77 | 27 | 106 | 583 | ▲+32
Submittals · 451
▲ +21 since yesterday
Chart: 
| Civil | Structural | Mechanical | Electrical | Instrumentation
Approved | 83 | 54 | 73 | 63 | 19
Resubmit | 15 | 10 | 17 | 13 | 4
Rejected | 5 | 3 | 6 | 5 | 1
Under Review | 19 | 13 | 22 | 18 | 8
Discipline | Approved | Resubmit | Rejected | Review | Total | Change
Civil | 83 | 15 | 5 | 19 | 122 | ▲+5
Structural | 54 | 10 | 3 | 13 | 80 | ▲+4
Mechanical | 73 | 17 | 6 | 22 | 118 | ▲+5
Electrical | 63 | 13 | 5 | 18 | 99 | ▲+5
Instrumentation | 19 | 4 | 1 | 8 | 32 | ▲+2
Overall | 292 | 59 | 20 | 80 | 451 | ▲+21
Notes: Total per discipline = Approved + Resubmit + Rejected + Under Review.

## Slide 3: Document types & approved revisions
Alpha District Development · 18-10-2026
Documents by type (cumulative)
Chart: 
| Drawings ▲+32 | Material Submittals ▲+11 | Method Statements ▲+4 | ITP ▲+4 | RFIs ▲+9 | Procedures ▲+1 | Calculations ▲+2 | Vendor Documents ▲+4
Current | 583 | 221 | 100 | 78 | 197 | 43 | 37 | 68
Arrow after the type = change since yesterday.
Approved by revision (% of overall cum.)
Chart: 
| Drawing rev 0 | Drawing rev 1 | Drawing rev 2 | Submittal rev 0 | Submittal rev 1 | Submittal rev 2
% of overall cum. | 24.2 | 9.5 | 2.4 | 18.4 | 7.9 | 1.9
Approved: 665 documents
Share is measured against 1,034 cumulative documents (Drawings + Submittals).
Notes: % of overall cum. = current approved / (Drawings total + Submittals total).

## Slide 4: Submission review: pending days
Alpha District Development · 18-10-2026
CLIENT · PENDING
127
13 pending ≥ 31 days
ALGIHAZ · PENDING
80
9 pending ≥ 31 days
SUPPLIER · PENDING
57
9 pending ≥ 31 days
ALL PARTIES · ≥ 31 DAYS
31
of 264 pending
How long items have been pending
Chart: 
| Client | Algihaz | Supplier
≤7 days | 75 | 49 | 29
8–30 days | 39 | 22 | 19
≥31 days | 13 | 9 | 9
Items pending ≥ 31 days, by review status
Chart: 
| Under review | Status A | Status B | Status C | Status D | Status E
Client | 10 | 2 | 1 | 0 | 0 | 0
Algihaz | 8 | 0 | 1 | 0 | 0 | 0
Supplier | 6 | 2 | 1 | 0 | 0 | 0
Notes: Pending days buckets: up to 7 days, 8 to 30 days, 31 days and above. Zero values are hidden in the right chart.