| ALGIHAZ · DAILY DOCUMENT GOVERNANCE REPORT Alpha District Development AGH-ALPHA · Cost centre CC-3107 Project team: PM – S. Rahman ¦¦ PE – M. Khan ¦¦ DC – A. Nair | REPORT DATE 18-10-2026 |
| --- | --- |

| ADDED SINCE YESTERDAY (Current − Yesterday) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Total | Approved | Resubmit | Rejected | Under Review |
| Submittals | +21 | +11 | +4 | +1 | +5 |
| Drawings | +32 | +16 | +4 | +2 | +10 |
| Submission total | +53 | +27 | +8 | +3 | +15 |

| CUMULATIVE DETAILS (till report date) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Total | Approved | Resubmit | Rejected | Under Review |
| Submittals | 451 | 292 | 59 | 20 | 80 |
| Drawings | 583 | 373 | 77 | 27 | 106 |
| Submission total | 1,034 | 665 | 136 | 47 | 186 |

Submission total = Drawings + Submittals. “Added since yesterday” shows how many documents moved into each status today; “Cumulative” is the position as on the report date.

| Approved share 64.3% 665 documents · ▲ +27 | Pending ≥ 31 days 31 of 264 pending reviews | Correspondence out / in 318 / 291 ▲ +6 / ▲ +6 today | Pending · all parties 264 Client 127 · Algihaz 80 · Supplier 57 |
| --- | --- | --- | --- |

# 01   Project Details

| Project code | AGH-ALPHA | Project name | Alpha District Development |
| --- | --- | --- | --- |
| Report date | 18-10-2026 | Cost centre | CC-3107 |
| Project manager | S. Rahman | Project engineer | M. Khan |
| Document controller | A. Nair |  |  |

If this is the first report for the project, a notice appears here: “First report for this project – no earlier submission exists, so Yesterday values start from zero.”

# 02   Daily Submission — Drawings & Submittals by Discipline

Cumulative figures as on the report date. The small figure under each count is the change since yesterday (Current − Yesterday). Total = Approved + Resubmit + Rejected + Under Review.

Drawings

| Discipline | Approved | Resubmit | Rejected | Under Review | Total yesterday | Total current | Change |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Civil | 126 ▲ +6 | 26 ▲ +1 | 8 ● 0 | 33 ▲ +3 | 183 | 193 | ▲ +10 |
| Structural | 101 ▲ +3 | 20 ▲ +2 | 7 ▲ +1 | 24 ▲ +2 | 144 | 152 | ▲ +8 |
| Mechanical | 67 ▲ +3 | 14 ● 0 | 6 ▲ +1 | 21 ▲ +2 | 102 | 108 | ▲ +6 |
| Electrical | 58 ▲ +3 | 12 ▲ +1 | 4 ● 0 | 17 ▲ +1 | 86 | 91 | ▲ +5 |
| Instrumentation | 21 ▲ +1 | 5 ● 0 | 2 ● 0 | 11 ▲ +2 | 36 | 39 | ▲ +3 |
| Drawings overall | 373 ▲ +16 | 77 ▲ +4 | 27 ▲ +2 | 106 ▲ +10 | 551 | 583 | ▲ +32 |

Submittals

| Discipline | Approved | Resubmit | Rejected | Under Review | Total yesterday | Total current | Change |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Civil | 83 ▲ +3 | 15 ▲ +1 | 5 ● 0 | 19 ▲ +1 | 117 | 122 | ▲ +5 |
| Structural | 54 ▲ +2 | 10 ▲ +1 | 3 ● 0 | 13 ▲ +1 | 76 | 80 | ▲ +4 |
| Mechanical | 73 ▲ +3 | 17 ▲ +1 | 6 ● 0 | 22 ▲ +1 | 113 | 118 | ▲ +5 |
| Electrical | 63 ▲ +2 | 13 ▲ +1 | 5 ▲ +1 | 18 ▲ +1 | 94 | 99 | ▲ +5 |
| Instrumentation | 19 ▲ +1 | 4 ● 0 | 1 ● 0 | 8 ▲ +1 | 30 | 32 | ▲ +2 |
| Submittals overall | 292 ▲ +11 | 59 ▲ +4 | 20 ▲ +1 | 80 ▲ +5 | 430 | 451 | ▲ +21 |

Change colours: Approved ▲ green, Rejected ▲ red; all other changes grey (no good/bad judgement).

# 03   Document Types (Cumulative)

| Document type | Yesterday | Current | Change |
| --- | --- | --- | --- |
| Drawings | 551 | 583 | ▲ +32 |
| Material Submittals | 210 | 221 | ▲ +11 |
| Method Statements | 96 | 100 | ▲ +4 |
| ITP | 74 | 78 | ▲ +4 |
| RFIs | 188 | 197 | ▲ +9 |
| Procedures | 42 | 43 | ▲ +1 |
| Calculations | 35 | 37 | ▲ +2 |
| Vendor Documents | 64 | 68 | ▲ +4 |

Cumulative count of each document type as on the report date.

# 04   Approved Status by Revision

| Document type | Revision no. | Yesterday approved | Current approved | Change | % of overall cum. |
| --- | --- | --- | --- | --- | --- |
| Drawing | 0 | 241 | 250 | ▲ +9 | 24.2% |
| Drawing | 1 | 94 | 98 | ▲ +4 | 9.5% |
| Drawing | 2 | 22 | 25 | ▲ +3 | 2.4% |
| Submittal | 0 | 183 | 190 | ▲ +7 | 18.4% |
| Submittal | 1 | 80 | 82 | ▲ +2 | 7.9% |
| Submittal | 2 | 18 | 20 | ▲ +2 | 1.9% |

% of overall cum. = Current approved ÷ overall cumulative documents (Drawings total + Submittals total = 1,034).

# 05   Correspondence

| Type | Yesterday | Current | Change |
| --- | --- | --- | --- |
| Outgoing | 312 | 318 | ▲ +6 |
| Incoming | 285 | 291 | ▲ +6 |

# 06   Rejected Submissions

| Type | Yesterday | Current | Change |
| --- | --- | --- | --- |
| Drawing | 25 | 27 | ▲ +2 |
| Materials | 9 | 10 | ▲ +1 |
| Calculation | 4 | 4 | ● 0 |
| General | 6 | 6 | ● 0 |
| Total rejected | 44 | 47 | ▲ +3 |

Cumulative rejected submissions by type. An increase is shown in red.

# 07   Submission Review — Pending Days

Number of submissions still waiting at each party, grouped by how long they have been pending. Total = ≤7 days + 8–30 days + ≥31 days.

| Client · pending 127 13 pending ≥ 31 days | Algihaz · pending 80 9 pending ≥ 31 days | Supplier · pending 57 9 pending ≥ 31 days | All parties · ≥ 31 days 31 of 264 pending |
| --- | --- | --- | --- |

| Entity | Bucket | ≤7 days | 8–30 days | ≥31 days | Total |
| --- | --- | --- | --- | --- | --- |
| Client | UNDER REVIEW | 52 | 28 | 10 | 90 |
|  | STATUS A | 12 | 5 | 2 | 19 |
|  | STATUS B | 6 | 3 | 1 | 10 |
|  | STATUS C | 3 | 2 | 0 | 5 |
|  | STATUS D | 2 | 1 | 0 | 3 |
|  | STATUS E | 0 | 0 | 0 | 0 |
| Client total |  | 75 | 39 | 13 | 127 |
| Algihaz | UNDER REVIEW | 34 | 16 | 8 | 58 |
|  | STATUS A | 8 | 3 | 0 | 11 |
|  | STATUS B | 4 | 2 | 1 | 7 |
|  | STATUS C | 2 | 1 | 0 | 3 |
|  | STATUS D | 1 | 0 | 0 | 1 |
|  | STATUS E | 0 | 0 | 0 | 0 |
| Algihaz total |  | 49 | 22 | 9 | 80 |
| Supplier | UNDER REVIEW | 20 | 12 | 6 | 38 |
|  | STATUS A | 5 | 3 | 2 | 10 |
|  | STATUS B | 3 | 2 | 1 | 6 |
|  | STATUS C | 1 | 1 | 0 | 2 |
|  | STATUS D | 0 | 1 | 0 | 1 |
|  | STATUS E | 0 | 0 | 0 | 0 |
| Supplier total |  | 29 | 19 | 9 | 57 |
| All parties |  | 153 | 80 | 31 | 264 |

Column headings follow a traffic-light scale: ≤7 days green, 8–30 days amber, ≥31 days red. A ≥31 days cell is also highlighted when the count is above zero. Entity and all-party totals are added up by the report.

| PREPARED BY A. Nair Document Controller | SUBMITTED ON 18-10-2026 17:45 Time zone: organisation | REPORT ID DDG-20261018-AGH-ALPHA |
| --- | --- | --- |

FOR REVIEW ONLY — REMOVE BEFORE HAND-OVER

Display rules for the PDF generator

| Situation | How the report should display it |
| --- | --- |
| Summary bands (page 1) | Two matrices in this order: “Added since yesterday” then “Cumulative”. Rows: Submittals, Drawings, Submission total (= Drawings + Submittals). Columns: Total, Approved, Resubmit, Rejected, Under Review. Added values print with a sign (+3, −1, 0). |
| Pending-days headings | ≤7 days green, 8–30 days amber, ≥31 days red (same on every table and on the dashboard). |
| First report for the project | Show a shaded notice in section 01: “First report for this project – no earlier submission exists, so Yesterday values start from zero.” All changes then equal the current value. |
| Zero-filled sections | Print zeros as 0. Do not hide the table or replace it with “N/A”. |
| Change since yesterday | Change = Current − Yesterday. Format ▲ +n, ▼ −n or ● 0. |
| Change colours | Approved ▲ green, ▼ red. Rejected ▲ red, ▼ green. Everything else grey. |
| Total (per discipline) | Read the form’s auto-calculated Total (Approved + Resubmit + Rejected + Under Review). |
| Overall rows | Drawings and Submittals overall totals come from the form. Overall Approved, Resubmit, Rejected and Under Review sums are added up by the report. |
| % of overall cum. | Current approved ÷ (Drawings total + Submittals total). One decimal. Show 0.0% if the denominator is 0. |
| Pending-days totals | Row Total comes from the form. Entity totals and the all-party row are added up by the report. |
| ≥ 31 days cell | Pink fill and bold when above zero. |
| No revision rows | Print one line “No revision rows added”. |
| Dates and numbers | Dates DD-MM-YYYY. Thousands separator on counts of 1,000 and above. Percentages one decimal. |
| Not printed | Template “Import workbook” and “Zero-fill authorized sections” are screen functions. |

Sample data is illustrative. Figures in “Prepared by”, “Submitted on” and “Report ID” are placeholders; see the mapping workbook for their source.