| ALGIHAZ · QA/QC MONTHLY METRICS REPORT Al Nakheel Commercial Complex Cost centre CC-2041 | REPORTING PERIOD October 2026 |
| --- | --- |

MONTH AT A GLANCE

| PQI · Acc. till this month 90.4 ▲ +1.7 pts vs last month | Open External NCRs 3 3 issued · 4 closed | Open Internal NCRs 5 9 issued · 8 closed | Quality manpower 11 5 departments |
| --- | --- | --- | --- |
| RFI closure · this month 95.2% 118 of 124 closed | RMI closure · this month 94.1% 80 of 85 closed | MIRN closure · this month 88.4% 38 of 43 closed | Toolbox talk manhours 48.00 8 talks · 192 attendees |

# 01   Quality Assessment Brief

October delivered stable quality performance. The accumulated Project Quality Index rose to 90.4 (▲ 1.7 pts; this month’s score 93.2), supported by higher RFI and RMI closure. External NCR closure improved to 85.7% accumulated; 3 External NCRs remain open, none older than 60 days. Internal NCR closure dipped by 0.3 pp as 9 NCRs were raised against 8 closed, mainly concrete finishing and MEP sleeve coordination. 5 MIRNs recorded overage, shortage or damage, and 6 items are held in quarantine pending supplier response. November focus: close the 16–60 day NCR backlog, clear quarantined items, and prepare for the internal audit scheduled on 18-12-2026.

✔  Reviewed and confirmed by the submitter

# 02   Project & Reporting Details

Project

| Project name | Al Nakheel Commercial Complex | Reporting period | October 2026 |
| --- | --- | --- | --- |
| Cost centre | CC-2041 | Report type | Monthly QA/QC Metrics |

Project Quality Plan (PQP)

| PQP status | Approved B | PQP submission date | 12-03-2026 |
| --- | --- | --- | --- |
| PQP approval date | 28-03-2026 |  |  |

Submission date reads “Not applicable” while the PQP is Under Preparation or unset. Approval date applies only to Approved A, B or C.

Last report sent to client

| Reference no. | ALG-NKC-QAR-2026-09 | Report date (from) | 01-09-2026 |
| --- | --- | --- | --- |
| Report date (to) | 30-09-2026 |  |  |

# 03   Meetings Conducted

| Meeting type | Date | Participants | Key outcome |
| --- | --- | --- | --- |
| Weekly Quality Review | 07-10-2026 | Client QA, PM, QA/QC Manager | NCR ageing reviewed; 3 actions assigned |
| Subcontractor Quality Briefing | 12-10-2026 | MEP & Civil subcontractors, QC team | Sleeve coordination checklist issued |
| Monthly Client Quality Meeting | 20-10-2026 | Client, PM, QA/QC Manager | September report accepted; PQI trend noted |
| Management Review | 27-10-2026 | Project Director, QA/QC Manager | Resources and Q4 audit plan confirmed |

4 meetings conducted this month. If none were added, this section reads “No meeting added”.

# 04   QMS Internal Audit

| Internal audit conducted | Yes | Last audit date | 18-09-2026 |
| --- | --- | --- | --- |
| Next audit date | 18-12-2026 |  |  |

# 05   Quality Manpower

| Department | Nos. | Client approval required? |
| --- | --- | --- |
| QA/QC Manager | 1 | Yes |
| Senior QC Engineer | 2 | Yes |
| QC Inspector (Civil) | 4 | Yes |
| QC Inspector (MEP) | 3 | Yes |
| Document Controller | 1 | No |
| Total manpower | 11 |  |

# 06   QA/QC Metrics — NCR, RFI & RMI

| Measure | External NCR | Internal NCR | RFI | RMI |
| --- | --- | --- | --- | --- |
| UP TO LAST MONTH |  |  |  |  |
| Accumulated issued | 18 | 42 | 640 | 410 |
| Closed | 14 | 38 | 628 | 401 |
| Cumulative closure % | 77.8% | 90.5% | 98.1% | 97.8% |
| THIS MONTH |  |  |  |  |
| Issued this month | 3 | 9 | 112 | 76 |
| Closed this month | 4 | 8 | 118 | 80 |
| Closure rate this month | 57.1% | 61.5% | 95.2% | 94.1% |
| UP TO THIS MONTH |  |  |  |  |
| Accumulated issued | 21 | 51 | 752 | 486 |
| Closed | 18 | 46 | 746 | 481 |
| Cumulative closure % | 85.7% | 90.2% | 99.2% | 99.0% |
| MOVEMENT |  |  |  |  |
| Variance vs last month | ▲ +7.9 pp | ▼ −0.3 pp | ▲ +1.1 pp | ▲ +1.2 pp |
| Open items now | 3 | 5 | n/a | n/a |

Cumulative closure % = closed ÷ accumulated issued (100% when nothing issued). Closure rate this month = closed this month ÷ (open at start of month + issued this month). Variance = change in cumulative closure %, in percentage points (pp). Open count and ageing are tracked for NCRs only.

Open NCR ageing

| NCR type | 0–15 days | 16–30 days | 31–60 days | > 60 days | Total aged | Total vs Open |
| --- | --- | --- | --- | --- | --- | --- |
| External NCR | 1 | 1 | 1 | 0 | 3 | ✔ 3 / 3 |
| Internal NCR | 2 | 2 | 1 | 0 | 5 | ✔ 5 / 5 |

Age is counted in days since the NCR was issued. “Total vs Open” compares the ageing total with the Open NCR count and turns red if they differ.

# 07   Project Quality Index (PQI)

| Acc. till last month 88.7 cumulative index | Acc. till this month 90.4 cumulative index | Variance +1.7 ▲ improved vs last month | This month score 93.2 this month only |
| --- | --- | --- | --- |

| Average of all projects | Pending 6 of 9 active projects have a valid report (3 pending) The average uses submitted/approved reports for this period only and stays pending until every active project has reported. |
| --- | --- |

PQI is calculated by the system from External NCR, Internal NCR, RFI and RMI results and cannot be edited.

# 08   Material Inspection (MIRN)

| Measure | Till last month | This month | Till this month |
| --- | --- | --- | --- |
| MIRNs issued (accumulated) | 230 | 34 | 264 |
| MIRNs closed | 221 | 38 | 259 |
| Open MIRNs | 9 | — | 5 |
| Closure rate | 96.1% (cumulative) | 88.4% (month) | 98.1% (cumulative) |
| Variance vs prior cumulative rate | ▲ +2.0 pts |  |  |

Overage, Shortage, Damage & Defects (OSD)

| OSD available | Yes | MIRNs with OSD | 5 |
| --- | --- | --- | --- |
| Total overage qty | 12 | Total shortage qty | 30 |
| Total damage qty | 8 | Total defective qty | 4 |

OSD fields read “Not applicable” when OSD available is No.

Status of items in MIRNs

| Status tag | No. of items | Share of total |
| --- | --- | --- |
| Approved | 138 | 86.3% |
| On Hold / Quarantine | 6 | 3.8% |
| Rejected – Do Not Use | 3 | 1.9% |
| Rejected – Return to Supplier | 4 | 2.5% |
| Hazardous Material | 5 | 3.1% |
| Handle & Store with Care | 4 | 2.5% |
| Total | 160 | 100.0% |

✔  Status tags total 160 = Total items in MIRNs 160

# 09   Quality Toolbox Talks (QTBT)

| Measure | Till last month | This month | Till this month |
| --- | --- | --- | --- |
| Number of talks | 36 | 8 | 44 |
| Manhours | 54.00 | 48.00 | 102.00 |
| Attendees (this month) | — | 192 | — |
| Duration per talk (minutes) | — | 15 | — |

Manhours this month = attendees × duration (minutes) ÷ 60.

# 10   Document Status — Drawings & Submittals

| Type | Approved | Re-submitted | Rejected | Under review | Total | Client review (days) | Algihaz review (days) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Drawings | 46 | 12 | 5 | 18 | 81 | 6.4 | 2.8 |
| Submittals | 38 | 9 | 4 | 14 | 65 | 7.2 | 3.1 |

Review times are averages in days. Total is the sum of the four status counts.

| Drawings remarks | Structural shop drawings for Level 3 slab pending client comments; MEP coordination set re-submitted after clash resolution. |
| --- | --- |
| Submittals remarks | Façade glazing samples rejected for colour tolerance; revised samples due next month. |

# 11   QMS Reports

| Report | Reference no. | Date | Remarks |
| --- | --- | --- | --- |
| Document Control Audit Report | QMS-DC-2026-10 | 22-10-2026 | Closed – no findings |
| Corrective Action Register | QMS-CAR-2026-10 | 25-10-2026 | 2 actions open |
| Management Review Minutes | QMS-MRM-2026-10 | 27-10-2026 | Issued |

If no rows were added, this section reads “No QMS report rows added”.

| CONFIRMATION ✔ Reviewed and confirmed | SUBMITTED BY Sample User QA/QC Manager | SUBMITTED ON 31-10-2026 Report ID QAQC-2026-10-NKC |
| --- | --- | --- |

FOR REVIEW ONLY — REMOVE BEFORE HAND-OVER

Display rules for the PDF generator

| Situation | How the report should display it |
| --- | --- |
| PQP Under Preparation / unset | PQP submission date and approval date → “Not applicable”. |
| PQP Approved A / B / C | Show submission date and approval date. |
| Internal audit conducted = No | Last and next audit dates → “Not applicable”. |
| No meetings added | Single line: “No meeting added”. Hide the table header. |
| No QMS report rows added | Single line: “No QMS report rows added”. |
| Nothing issued (0 / 0) | Percentages show 100.0%, per system rule. Variance shows “● 0.0 pp (no change)”. |
| Ageing total ≠ Open NCRs | “Total vs Open” cell turns red (✖ x / y). Report still prints. |
| Status tags total ≠ Total items | Reconciliation line turns red (✖). Report still prints. |
| OSD available = No | OSD quantity fields → “Not applicable”. |
| Average of all projects | Shows “Pending – x of y active projects reported” until all active projects have a valid report; then shows the number. |
| Variance colour | Green ▲ = improvement, red ▼ = decline, grey ● = no change. Same rule everywhere. |
| Dates and decimals | Dates DD-MM-YYYY. Percentages 1 decimal. Manhours 2 decimals. Review days 1 decimal. |

Sample data is illustrative. Quality Assessment Brief is placed first (after the glance tiles) so executives read it before the detail; it is still entered last in the form.