## Slide 1: Quality overview
Al Nakheel Commercial Complex · October 2026
PQI · ACCUMULATED
90.4
▲ +1.7 pts vs last month
OPEN NCRs
8
Ext 3 · Int 5
RFI CLOSURE · MONTH
95.2%
118 of 124 closed
MIRN CLOSURE · MONTH
88.4%
38 of 43 closed
QTBT MANHOURS
48.00
8 talks · 192 attendees
Cumulative closure %: last month vs this month
Chart: 
| Ext NCR | Int NCR | RFI | RMI | MIRN
Last month | 77.8 | 90.5 | 98.1 | 97.8 | 96.1
This month | 85.7 | 90.2 | 99.2 | 99 | 98.1
Project Quality Index
Chart: 
| Score | Gap
PQI | 90.4 | 9.6
90.4
This month 93.2
Portfolio avg: Pending (6 of 9)
Governance
PQP status
Approved B
Last audit
18-09-2026
Next audit
18-12-2026
Meetings held
4
Manpower
11 people
Quality assessment brief
Stable quality performance; accumulated PQI up 1.7 pts to 90.4. External NCR closure improved to 85.7% (3 open, none beyond 60 days). Internal NCR closure dipped 0.3 pp (9 raised vs 8 closed). 6 items in quarantine pending supplier response. Next: close the 16–60 day NCR backlog and clear quarantined items.
Notes: Overview of the October 2026 QA/QC metrics. Sample data. PQI donut shows accumulated PQI; this-month score and portfolio average status are noted beneath it.

## Slide 2: NCR, RFI & RMI performance
Al Nakheel Commercial Complex · October 2026
External NCR
57.1%
closure rate this month
Cumulative 85.7% ▲ +7.9 pp
3 issued · 4 closed · 3 open
Internal NCR
61.5%
closure rate this month
Cumulative 90.2% ▼ −0.3 pp
9 issued · 8 closed · 5 open
RFI
95.2%
closure rate this month
Cumulative 99.2% ▲ +1.1 pp
112 issued · 118 closed
RMI
94.1%
closure rate this month
Cumulative 99.0% ▲ +1.2 pp
76 issued · 80 closed
NCRs: issued vs closed
Chart: 
| External | Internal
Issued | 3 | 9
Closed | 4 | 8
RFI & RMI: issued vs closed
Chart: 
| RFI | RMI
Issued | 112 | 76
Closed | 118 | 80
Open NCR ageing (days)
Chart: 
| External | Internal
0–15 days | 1 | 2
16–30 days | 1 | 2
31–60 days | 1 | 1
> 60 days | 0 | 0
✔ Ageing totals match open NCRs
Notes: Closure rate this month = closed this month / (open at start + issued). Cumulative % = closed / accumulated issued. pp = percentage points.

## Slide 3: Material inspection (MIRN)
Al Nakheel Commercial Complex · October 2026
MIRNs ISSUED · MONTH
34
264 accumulated
MIRNs CLOSED · MONTH
38
259 accumulated
CLOSURE RATE · MONTH
88.4%
5 MIRNs open
CUMULATIVE CLOSURE
98.1%
▲ +2.0 pts vs last month
Status of items in MIRNs (160 items)
Chart: 
| Approved | On Hold / Quarantine | Rejected – Do Not Use | Rejected – Return to Supplier | Hazardous Material | Handle & Store with Care
Items | 138 | 6 | 3 | 4 | 5 | 4
160
items
Approved
138
On Hold / Quarantine
6
Rejected – Do Not Use
3
Rejected – Return to Supplier
4
Hazardous Material
5
Handle & Store with Care
4
Overage, shortage, damage & defects
Chart: 
| Overage | Shortage | Damage | Defective
Qty | 12 | 30 | 8 | 4
5 MIRNs with OSD recorded
Notes: OSD = Overage, Shortage, Damage. Quantities are totals entered on the form. Status tags total must equal total items in MIRNs.

## Slide 4: Training & document status
Al Nakheel Commercial Complex · October 2026
TALKS · MONTH
8
44 accumulated
ATTENDEES · MONTH
192
15 min per talk
MANHOURS · MONTH
48.00
54.00 before
ACC. MANHOURS
102.00
44 talks to date
Drawings & submittals by status
Chart: 
| Drawings | Submittals
Approved | 46 | 38
Re-submitted | 12 | 9
Rejected | 5 | 4
Under review | 18 | 14
Average review time (days)
Chart: 
| Drawings | Submittals
Client | 6.4 | 7.2
Algihaz | 2.8 | 3.1
Notes: Manhours this month = attendees x duration (minutes) / 60.

## Slide 5: Governance & resources
Al Nakheel Commercial Complex · October 2026
Project Quality Plan
Status
Approved B
Submitted
12-03-2026
Approved
28-03-2026
QMS internal audit
Conducted
Yes
Last audit
18-09-2026
Next audit
18-12-2026
Last report sent to client: ALG-NKC-QAR-2026-09 (01-09-2026 to 30-09-2026)
Meetings conducted (4)
Weekly Quality Review
07-10-2026
NCR ageing reviewed; 3 actions assigned
Subcontractor Quality Briefing
12-10-2026
Sleeve coordination checklist issued
Monthly Client Quality Meeting
20-10-2026
September report accepted; PQI trend noted
Management Review
27-10-2026
Resources and Q4 audit plan confirmed
QMS reports (3)
Document Control Audit Report
22-10-2026
QMS-DC-2026-10 · Closed – no findings
Corrective Action Register
25-10-2026
QMS-CAR-2026-10 · 2 actions open
Management Review Minutes
27-10-2026
QMS-MRM-2026-10 · Issued
Quality manpower
Chart: 
| QA/QC Manager | Senior QC Engineer | QC Inspector (Civil) | QC Inspector (MEP) | Document Controller
Nos | 1 | 2 | 4 | 3 | 1
11 total
Client approval required for all except Document Controller
Notes: Manpower, meetings, QMS reports and audit dates come straight from form sections 3-6 and 12.